## Discovery
Category | Task | Status | Phase
Identity | Export Full User List | Planned | Discovery
Identity | Identify shared accounts, service accounts, and aliases | Planned | Discovery
Identity | Identify group memberships, distribution lists, and shared mailboxes | Planned | Discovery
Identity | Identify current admin roles and permissions | Planned | Discovery
Identity | Identify orphaned/unused accounts, and what to do with them | Planned | Discovery
Endpoint | Document current device management system | Planned | Discovery
Endpoint | Check for domain join, Intune, MDM enrollment etc | Planned | Discovery
Endpoint | Identity Operating System Versions | Planned | Discovery
Endpoint | Identify specialty devices (printers, kiosks, shared PCs etc) | Planned | Discovery
File Storage/Collaboration | Audit cloud/local storage platforms and structure | Planned | Discovery
File Storage/Collaboration | Review folder ownership and sharing structure | Planned | Discovery
File Storage/Collaboration | Evaluate storage usage by department/user | Planned | Discovery
File Storage/Collaboration | Flag sensitive or regulated data | Planned | Discovery
Email and Calendars | Determine current email platform | Planned | Discovery
Email and Calendars | Identify shared mailboxes, distribution lists, delegated access, calendar shares | Planned | Discovery
Email and Calendars | Inventory archive mailboxes or vaults | Planned | Discovery
Email and Calendars | Check email routing or 3rd party gateways | Planned | Discovery
Email and Calendars | Export mailbox list with sizes | Planned | Discovery
Email and Calendars | Document forwarding rules on inboxes | Planned | Discovery
Security and Compliance | Document existing stack (EDR, Spam filters, Firewall etc) | Planned | Discovery
Security and Compliance | Identify compliance requirements (HIPAA, SOC2, retention policies) | Planned | Discovery
Apps and Integrations | Identity SaaS Tools and Integrations | Planned | Discovery
Apps and Integrations | Identify apps using SSO or Oauth | Planned | Discovery
DNS and Infrastructure | Verify access to DNS and registrar | Planned | Discovery
DNS and Infrastructure | Identify domains/subdomains in use | Planned | Discovery
Stakeholder Input | Confirm points of contact per department | Planned | Discovery
Stakeholder Input | Gather customer workflows, calendar sharing, or file permissions to preserve/migrate | Planned | Discovery

## Pre-Migration
Category | Task | Status | Phase | Reference
Identity & Access (Entra ID) | Define user and department-based Entra ID groups | Planned | Pre-Migration | 1.2
Identity & Access (Entra ID) | Create Conditional Access baseline policies | Planned | Pre-Migration
Identity & Access (Entra ID) | Assign admin roles to separate accounts | Planned | Pre-Migration
Identity & Access (Entra ID) | Enable MFA for all users | Planned | Pre-Migration
Identity & Access (Entra ID) | Enable self service password resetfor all standard users | Planned | Pre-Migration
Identity & Access (Entra ID) | Block legacy authentication protocols | Planned | Pre-Migration
Identity & Access (Entra ID) | Audit risky sign-in and login failure logs | Planned | Pre-Migration
Identity & Access (Entra ID) | Block Mobile Login | Planned | Pre-Migration
Identity & Access (Entra ID) | Disable user consent to apps | Planned | Pre-Migration
Microsoft 365 Core | Audit stale Entra groups and DLs | Planned | Pre-Migration
Microsoft 365 Core | Create and configure distribution lists | Planned | Pre-Migration
Microsoft 365 Core | Create and configure shared mailboxes | Planned | Pre-Migration
Microsoft 365 Core | Set tenant-wide 6-year retention policy | Planned | Pre-Migration
Microsoft 365 Core | Set incoming external sender warning in MailFlow Rules | Planned | Pre-Migration
Microsoft 365 Core | Catch-All Address for ghost mailboxes | Planned | Pre-Migration
Microsoft 365 Core | Block user generated auto forwarding rules | Planned | Pre-Migration
Microsoft 365 Core | Set external sending tooltip in DLP I in Purview | Planned | Pre-Migration
Endpoint Management (Intune) | Setup Device Configuration Profiles | Planned | Pre-Migration
Endpoint Management (Intune) | Setup User Configuration Profiles | Planned | Pre-Migration
Endpoint Management (Intune) | Deploy Default Security Baseline | Planned | Pre-Migration
Endpoint Management (Intune) | Deploy M365 apps to all devices (Policy) | Planned | Pre-Migration
Endpoint Management (Intune) | Auto-enroll Windows devices via Autopilot (Policy) | Planned | Pre-Migration
Endpoint Management (Intune) | Push OneDrive auto sign-in (Policy) | Planned | Pre-Migration
Endpoint Management (Intune) | Block USB storage on managed devices with Exceptions Group (Policy) | Planned | Pre-Migration
Endpoint Management (Intune) | Deploy compliance policy: encryption required | Planned | Pre-Migration
Endpoint Security (Defender) | Create and assign AV policy via Intune | Planned | Pre-Migration
Endpoint Security (Defender) | Enable EDR in block mode | Planned | Pre-Migration
Endpoint Security (Defender) | Enable ASR rules | Planned | Pre-Migration
Endpoint Security (Defender) | Onboard all enrolled devices to Defender | Planned | Pre-Migration
Endpoint Security (Defender) | Deploy Defender for Office 365 Protections | Planned | Pre-Migration
SharePoint & Drive Migration | Create shared company-wide site for cross-dept docs | Planned | Pre-Migration
SharePoint & Drive Migration | Enable SharePoint version history | Planned | Pre-Migration
SharePoint & Drive Migration | Create SharePoint sites for each department | Planned | Pre-Migration
SharePoint & Drive Migration | Assign groups to SharePoint site permissions | Planned | Pre-Migration
SharePoint & Drive Migration | Apply OneDrive retention policy | Planned | Pre-Migration
SharePoint & Drive Migration | Audit existing cloud and local file storage | Planned | Pre-Migration
Azure | Configure and create unified audit log automation | Planned | Pre-Migration
DNS & Infrastructure | Confirm domain ownership in O365 | Planned | Pre-Migration
DNS & Infrastructure | Enable SPF, DKIM, and DMARC | Planned | Pre-Migration

## Migration
Category | Task | Status | Phase
SharePoint & Drive Migration | Migrate personal Drive files to OneDrive | Planned | Migration
SharePoint & Drive Migration | Migrate Static filestores in Drive to appropriate Sharepoint folder | Planned | Migration
SharePoint & Drive Migration | Migrate shared departmental folders to SharePoint | Planned | Migration
SharePoint & Drive Migration | Migrate RingCentral files to archive site | Planned | Migration
Microsoft 365 Core | Pre-migrate mail with Microsoft Migration Tool | Planned | Migration
Microsoft 365 Core | Delta Sync mail prior to cutover with validation | Planned | Migration
Microsoft 365 Core | Cutover MX records and validate SPF/DKIM/DMARC | Planned | Migration
Microsoft 365 Core | Test send/receive mail flow post cutover | Planned | Migration

## Post-Migration
Category | Task | Status | Phase | Phase
Compliance | Create final documentation for HIPAA binder | Planned | Post-Migration
Compliance | Document terminated user data access policy | Planned | Post-Migration
Compliance | Test eDiscovery access to archived/inactive mailboxes | Planned | Post-Migration
User Comms | Send department cutover announcements | Planned | Post-Migration
User Comms | Prepare end-user FAQ and cheat sheet | Planned | Post-Migration
User Comms | Create template email for post-migration fallback | Planned | Post-Migration
User Comms | Schedule post-migration training sessions | Planned | Post-Migration
SharePoint & Drive Migration | Confirm access requirements | Planned | Post-Migration
Compliance | Export baseline audit logs from Purview | Planned | Pre-Migration